## Ringkasan Mandays
Ringkasan Mandays per Tahapan
Tahapan | Mandays (MD)
Perencanaan & Analisis | 4.5
Development Sistem | 12.5
QA & Deployment | 17
Post-Deployment & Management | 8
Total
Ringkasan Mandays per Peran
Peran | Mandays (MD)
Technical Project Coordinator | 12
Quality Assurance | 12
Backend Engineer | 10.5
Frontend Engineer | 2.5
DevOps Engineer | 5
Total

## CR-20260729-001-Analysis
No | Proses | Deskripsi | Days | People | Mandays | Technical Project Coodinator | Product Designer | Quality Assurance | Backend Engineer | Frontend Engineer | Data Entry | DevOps Engineer
1 | Perencanaan & Analisis | Analisis awal, requirement gathering, dan koordinasi dengan BSB |  |  | 4.5 | 4 | 0 | 0 | 0.5 | 0 | 0 | 0
1.1 | Analisis Teknis & Koordinasi Core Banking BSB | Analisis teknis & koordinasi core banking terkait constraint panjang field | 1.5 | 1 | 1.5 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0
1.2 | Finalisasi Dokumen CR & Penawaran | Penyusunan dokumen Change Request dan penawaran resmi | 3 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
2 | Development Sistem (Delta TSD v0.8.6 - v0.8.8) | Fase implementasi pengembangan sistem delta TSD v0.8.6 - v0.8.8 |  |  | 12.5 | 0 | 0 | 0 | 10 | 2.5 | 0 | 0
2.1 | Epic 1: Backend Integration | Pengembangan modul integrasi backend API Tapera |  |  | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0
2.1.1 | Route Alignment (12 Endpoints) | Perubahan path endpoint dari /angsuran/ ke /jadwal-angsur/ (12 endpoint) | 1.5 | 1 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0
2.1.2 | DTO, Validation & DB Migration (19 Fields) | Update panjang maksimum field (19 field) & hapus field tidak terpakai | 1.5 | 1 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0
2.1.3 | Stok Rumah Service (List & Detail) | Penyesuaian respons Stok Rumah (List & Detail) dengan field baru | 2 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0
2.1.4 | Backend Unit Testing & Integration Test | Pengujian unit dan integrasi di sisi backend | 5 | 1 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0
2.2 | Epic 2: Frontend Penyesuaian | Penyesuaian di sisi frontend aplikasi |  |  | 2.5 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
2.2.1 | Model House & Eligibility Field Update | Update model House & eligibility field sesuai spesifikasi TSD | 1.25 | 1 | 1.25 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0
2.2.2 | Dropdown Pekerjaan Pemohon & UI Validation | Penyesuaian dropdown Pekerjaan Pemohon dan validasi UI | 0.75 | 1 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0
2.2.3 | Frontend Testing & Type Check | Pengujian frontend, type checking, dan validasi tampilan | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
3 | QA & Deployment | Fase pengujian menyeluruh (QA) dan deployment ke production |  |  | 17 | 0 | 0 | 12 | 0 | 0 | 0 | 5
3.1 | Regression Testing, UAT/VIT & Support | Regression testing, UAT/VIT bersama BSB dan pendampingan | 12 | 1 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0
3.2 | Deployment to Staging & Production + Rollback Plan | Deployment ke staging/production dan penyiapan rollback plan | 5 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | Post-Deployment & Management | Fase pasca deployment, manajemen proyek, dan dokumentasi |  |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Project Management (Monitoring & Meeting) | Project management, monitoring, koordinasi, dan meeting rutin | 5 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Pendampingan Pasca-Deployment & Dokumentasi | Pendampingan pasca-deployment dan pembaruan dokumentasi | 3 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| GRAND TOTAL | Total keseluruhan mandays pengerjaan Change Request |  |  | 42 | 12 | 0 | 12 | 10.5 | 2.5 | 0 | 5

## Timeline
Aktivitas / Tahapan | Hari 1 | Hari 2 | Hari 3 | Hari 4 | Hari 5 | Hari 6 | Hari 7 | Hari 8 | Hari 9 | Hari 10 | Hari 11 | Hari 12 | Hari 13 | Hari 14 | Hari 15
Analisa & Perencanaan | bar: Hari 1 to Hari 4
Development (Backend) | bar: Hari 2 to Hari 9
Development (Frontend) | bar: Hari 2 to Hari 7
Internal Testing | bar: Hari 8 to Hari 12
Regression Testing & UAT | bar: Hari 11 to Hari 14
Deployment & DevOps | bar: Hari 14 to Hari 15
Manajemen Proyek & Dokumentasi | bar: Hari 1 to Hari 15
Keterangan: | Hari 1: █ = Masa Pengerjaan Aktif